# Leave-behind: one Virley experience in every channel

Oct 21, 2026 ·

V&S can return to leading growth by delivering one Virley experience in every channel, proven in London in year one and scaled after.

## The storyline

| Main idea | Supporting ideas | Facts to date |
| --- | --- | --- |
| The sales push is capped by how the experience is delivered and run | Online delivery and returns have operational issues; foundations are fragmented across people, stock data and IT | Growth below market, margins falling, IT director seat empty for 6+ months |
| One Virley experience across stores and online is the growth idea | Know every client and serve them the same everywhere; stores stage the experience and online extends it | Millennials and Gen Z about 45% of luxury; omnichannel brands grow 9.5% a year vs 3.4% for single-channel |
| A phased plan proves it within a year and scales it after | Fix foundations, then prove the model in London; scale proven formats and time any web-only acquisition | £2bn and 10% targets to be validated by benchmarking against peers |

## Roadmap

First 100 days: foundations. Months 4 to 12: prove the model in London. Year 2: scale proven formats and decide on a web-only acquisition.

## Three decisions today

- Endorse the reframe to one Virley experience in every channel

- Agree to prove the model in the London flagship

- Name sponsors and an interim IT leader

## Next 30 days

- Benchmark V&S against peers

- Map the client journey and review the online report

- Build a store-level P&L baseline

- Hold a board alignment workshop

Market figures: Clarkston Consulting 2026; HUB Institute 2024, cited by Cegid. Draft for discussion, 27 October 2026.